## KormeeAutomationPlan
Sl. | Type | Issues | Business Unit | Planned Solution | Responsible | Delivery Time Line | Proposed Cost (BDT) | Remarks | 2020-01-07 | 2020-01-14 | 2020-01-21 | 2020-01-28 | 2020-02-04 | 2020-02-11 | 2020-02-18 | 2020-02-25 | 2020-03-03
1 | Allowance | Shift allowance (6th day allowance) | Celsius & Birichina | Kormee Shift mgt. module will be enabled for policy based allowance calculation. | CSL | 2020-01-16 | 20000 | 5 days per week | bar: 2020-01-07 to 2020-01-21
2 | Allowance | Salary adjustment of previous months | Celsius & Birichina | New Column for Arrear will be added in Salary Sheet and amount will be uploaded in Kormee through Excel | CSL | 2020-01-16 | 0 | Approval of all Monthly Salary Adjustment Issue | bar: 2020-01-07 to 2020-01-21
3 | Allowance | Adjustments related to any attendance corrections | Celsius & Birichina | Arrear will be added in Salary Sheet and amount will be uploaded in KORMEE through Excel | CSL | 2020-01-16 | 10000 | Approval of all Monthly Salary Adjustment Issue | 2020-01-28: *Not Required, as management don't permit any manual attendance correction
4 | Allowance | Machine allowance | Celsius | Will be managed though Incentive mgt solution. System Customization planned | CSL | 2020-01-22 | 0 | bar: 2020-01-07 to 2020-01-28
5 | Allowance | Machine allowance(Jumper allowance) | Birichina | KORMEE Salary Rule will be configured, with Salary Reports Integration. | CSL | 2020-01-16 | 0 | bar: 2020-01-07 to 2020-01-21
6 | Deductions | Advance deductions(EMI Based) | Celsius & Birichina | Kormee Loan Module Need to be enabled for EMI based deduction automation. | CSL | 2020-01-22 | 10000 | bar: 2020-01-07 to 2020-01-28
7 | Report | Maternity benefits (Actual) | Celsius & Birichina | Kormee Maternity Leave mgt. will be enabled for Maternity benefit calculation. | CSL | 2020-01-16 | 10000 | As per Govt. Law. Need Notification before/after of maternity leave | bar: 2020-01-07 to 2020-01-21
8 | Report | Maternity benefits (Buyer) | Celsius & Birichina | Kormee Maternity Leave mgt. will be enabled for Maternity benefit calculation. | CSL | 2020-01-16 | 10000 | As per Govt. Law | bar: 2020-01-07 to 2020-01-21
9 | Report | Disbursement of the final Service benefits | Celsius & Birichina | Kormee Final Settlement Module will be implemented | CSL | 2020-02-12 | 10000 | bar: 2020-01-07 to 2020-02-18
10 | Report | SUPPLEMENTARY SALARY SHEET | Celsius | Condition will be removed from Salary Process | CSL | 2020-01-13 | 0 | Salary is not processing in case present less than 5 days | bar: 2020-01-07 to 2020-01-14
11 | Report | Extra OT hide: 60h/W, 72h/W,84h/W, Actual | All | Job Card, Payslip, Salary Sheet, Bank Forwarding | CSL | 2020-02-23 | 80000 | bar: 2020-01-07 to 2020-02-25
12 | Report | Service Book | All |  | CSL | 2020-02-18 | 50000 | bar: 2020-01-07 to 2020-02-18
13 | Report | Long absent correspondence 3 reports | All | Letter 1: Will be issued 11th working day for continuous Absent (excluding W/H) Letter 2: After 10 days of issuing Letter 1 Letter 3: After 7 days of issuing Letter 2 | CSL | 2020-01-13 | 30000 | bar: 2020-01-07 to 2020-01-14
14 | Report | Increment Letter | All | New report design as per SQ given format | CSL | 2020-01-15 | 10000 | bar: 2020-01-07 to 2020-01-21
15 | Report | Promotion Letter | All | New report design as per SQ given format | CSL | 2020-01-15 | 10000 | bar: 2020-01-07 to 2020-01-21
16 | Report | Transfer Letter | All | New report design as per SQ given format | CSL | 2020-01-15 | 10000 | bar: 2020-01-07 to 2020-01-21
17 | Report | Floor Transfer Report |  |  | CSL | 2020-01-15 | 10000 | bar: 2020-01-07 to 2020-01-21
18 | Report | Appointment Letter Worker | All | New report design as per SQ given format | CSL | 2020-01-15 | 10000 | bar: 2020-01-07 to 2020-01-21
19 | Report | Appointment Letter Staff | All | New report design as per SQ given format | CSL | 2020-01-15 | 10000 | bar: 2020-01-07 to 2020-01-21
20 | Report | Individual Leave Register Report (form no 9) | All | New report design as per SQ given format | CSL | 2020-01-26 | 10000 | bar: 2020-01-07 to 2020-01-28
21 | Report | Salary Reconciliation Report | All | SQ will share the format | CSL | TBC | 20000
22 | Report | Separate column for the difference of payable gross & gross salary. | All | Adding Actual Gross Column in Salary Sheet | CSL | TBC | 0
23 | Report | English version of details payrolls. | All | One more salary sheet for Worker in English Version | CSL | TBC | 10000
24 | Report | Registering Certification Data | All | A query to generate Name, Father Name, National ID care wise Certification Info | CSL | TBC | 10000
25 | New feature function | Policy tagged interface (Shift allowance or if any) | All | New system feature development to define Policies in a single page with restriction in changing | CSL | 2020-01-29 | 30000 | bar: 2020-01-07 to 2020-02-04
26 | New feature function | Maternity Payment disbursement with Notification | All | New system feature development for notification service | CSL | 2020-02-24 | 50000 | bar: 2020-01-07 to 2020-01-28
27 | New feature function | Increment effective date from exact due date need to implement (DOJ to DOJ) | All | Automatic increment based on Policy for worker. Like after completion of 1 year auto increment of 5% | CSL | TBC | 30000
28 | New feature function | Recruitment Budget declaration & Control | All | Month wise budget declaration and recruitment control. | CSL | TBC | 100000
550000
Total Cost Summary:
| Total Costing (New Report, Interface, Report Modification) |  | 550000
| Implementation Cost (Per Unit=50,000) |  | 150000
| Emergency Development Cost |  | 50000
| Grand Total |  | 750000
In Word: Five Lac Eighty Thousand taka
Recruitment Alert Revision:
| a. 02 summary Reports (New Requirement) |  | 20,000/-
| b. 01 Details report New Requirement |  | 10,000/-
| c. 01 Details report Modification |  | 5,000/
| d. Attachment for mail body Modification |  | 5,000/-
| Grand Total |  | 40,000/-
Inword: Forty thousand Take only.
| Grand Total: |  | 790,000/-

## Detail Scope (hidden)
Meeting with KORMEE, Birichina & Celsius HR Team
Date: 13-Nov-19
Agenda: Details discussion of all issue and scope finalization
Manual Payments | Company | Policy | Current Practice | Planned Solution | Responsible | Remarks
Thursday Allow | Birichina | 1. Payment will be applicable in case Present in Offday | Manual Calculation | Kormee will come back with the proposed solution. | Kormee | Hamid will share the job card format by 16th Nov
|  | 2. If present 8:00-5:00 PM then => 1 day's Gross. Gross will be calculated 26 day basis |  | SQ will share Job card format with expected changes. | SQ
3. OT will be calculated after 5:00 PM. Rate will as per normal policy
4. Both Gross Salary & OT Amount will be display in the same column of Salary Sheet, that is :Thursday Allow"
Salary adjustment of previous months | Birichina | In case any unpaid or arrear amount needs to pay with this month. | There is no Salary Head for Arrear in Salary Sheet, So at present payment is manual | Need add Arrear column & Head in Salary Sheet | Kormee
Adjustments related to any attendance corrections | Birichina | Arrear due to any Attendance Correction | As above | Need add Arrear column & Head in Salary Sheet | Kormee
Incentive Calculation-Colblanc | Colblanc | Same As Birichina | Manual Calculation | Need to implement the existing Incentive System | SQ
Incentive Calculation-Celsius | Celsius | Arrear due to any Attendance Correction | Manual Calculation | Need to customize Incentive System with Celsius Policy | SQ
Tiffin Allowance | Celsius | Will be discussed in separate meeting with Celsius Unit-1 | Manual Calculation | Need to discuss further with Celsius-1 HR Team | SQ
Machine allowance-Birichina | Birichina | For Line- "Jumper": A category: 1000 tk B category: 750 tk C category: 500 tk This amount is fixed. No deduction for absent or new joiner. | Manual calculation. Allowance is with Thursday Allowance | Need to configure in Salary Rale, Need head in Salary Sheet & Pay Slip. | Kormee
Machine allowance-Celsius | Celsius | As per number of Machine Operated. | Manual Calculation | Inhouse development | SQ
Advance deductions | Birichina & Celsius | EMP basis loan. For MLV employee Loan Should not deduct No Interest | Manual Calculation | Loan Module: Impact in 1. Salary Sheet 2. Pay Slip New report: Monthly Loan Deduction Report | Kormee | Hamid & Shams will share the expected Monthly Loan Deduction Report format by 17th Nov
Maternity benefits | Birichina & Celsius | As per govt. Law | Manual | 1.Need to share format with formula to CSL for detail plan. 2. EL encashment amount will be uploaded in Kormee. 3. Two reports need to be developed: Actual & Buyer. This is for OT issue. | Kormee | Hamid & Shams will share the excel formats by 16th Nov
Disbursement of the final Service benefits | Birichina & Celsius | Postponed | Manual | HR team will share the detail policy in written. | SQ | Hamid & Shams will share the written policy in details. Accordingly further Skype call will be arranged(TBC)