## Ashiqur Rahman (hidden)
Resource
Ashiqur Rahman
SL | Project | Activity | Engagement % Per-Day | Work Hour | Work Minute (Per Day) | Weekly Total (Minutes) | Engagement Per-Day (Minutes) | 2020-12-12 | 2020-12-13 | 2020-12-14 | 2020-12-15 | 2020-12-16 | 2020-12-17 | 2020-12-18 | 2020-12-19 | 2020-12-20 | 2020-12-21 | 2020-12-22 | 2020-12-23 | 2020-12-24 | 2020-12-25 | 2020-12-26 | 2020-12-27 | 2020-12-28 | 2020-12-29 | 2020-12-30 | 2020-12-31 | Remaining (Hours) | End Date
1 | Visitor Approval System | Requirement Analysis | 25.28% | 9 | 540 | 2730 | 136.5 | 330 | 330 | 330 | 330 | 0 | 330 | 0 | 180 | 180 | 180 | 180 | 180 | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 2020-12-24
2 | Security Guard App | Development | 18.61% |  |  | 2010 | 100.5 | 60 | 60 | 60 | 60 | 0 | 60 | 0 | 60 | 60 | 60 | 60 | 60 | 60 | 0 | 225 | 225 | 225 | 225 | 225 | 225 | 28.5 | 2020-12-31
3 | Bill Management App | Requirement Analysis | 26.94% |  |  | 2910 | 145.5 | 60 | 60 | 60 | 60 | 0 | 60 | 0 | 210 | 210 | 210 | 210 | 210 | 210 | 0 | 225 | 225 | 225 | 225 | 225 | 225 | 43.5 | 2020-12-31
4 | Maintenance & Troubleshooting (Capex, ER, DEC Service Tracker, VAS, PMS, QMS, Hot Desking, IOU) | Troubleshooting | 9.444% |  |  | 1020 | 51 | 60 | 60 | 60 | 60 | 0 | 60 | 0 | 60 | 60 | 60 | 60 | 60 | 60 | 0 | 60 | 60 | 60 | 60 | 60 | 60 | - | -
5 | Others Project (Meeting, Presentation to Mgt) | Based on request | 4.722% |  |  | 510 | 25.5 | 30 | 30 | 30 | 30 | 0 | 30 | 0 | 30 | 30 | 30 | 30 | 30 | 30 | 0 | 30 | 30 | 30 | 30 | 30 | 30 | - | -
|  | Total | 85% | 9 | 540 | 9180 | 459 | 540 | 540 | 540 | 540 |  | 540 |  | 540 | 540 | 540 | 540 | 540 | 540 |  | 540 | 540 | 540 | 540 | 540 | 540
|  | Available | [5 empty] | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0

## Ashiqur Rahman (2)
Resource
Ashiqur Rahman
SL | Project | Activity | Engagement % Per-Day | Work Hour | Work Minute (Per Day) | Weekly Total (Minutes) | Engagement Per-Day (Minutes) | 2020-12-19 | 2020-12-20 | 2020-12-21 | 2020-12-22 | 2020-12-23 | 2020-12-24 | 2021-01-01 | 2021-01-02 | 2021-01-03 | 2021-01-04 | 2021-01-05 | 2021-01-06 | 2021-01-07 | 1900-02-05 | 1900-02-06 | 1900-02-07 | 1900-02-08 | 1900-02-09 | 1900-02-10 | Remaining (Hours) | End Date
1 | Visitor Approval System | Post Go-live Support | 0% | 9 | 540 | 0 | 0 | 450 | 420 | 435 | 330 | 390 | 390 | 0 | 0 | 435 | 360 | 330 | 330 | 390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-02-28
2 | Security Guard App | Development | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 2021-03-31
3 | Bill Management System | Development | 61.88% |  |  | 2005 | 334.1667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 60 | 0 | 0 | 0 | 525 | 490 | 520 | 470 | 39 | 2021-02-28
4 | AQL-API | Development | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-02-04
4 | Maintenance & Troubleshooting (Capex, ER, DEC Service Tracker, VAS, PMS, QMS, Hot Desking, IOU) | Troubleshooting | 3.086% |  |  | 100 | 16.6667 | 60 | 60 | 60 | 180 | 30 | 30 | 0 | 60 | 60 | 150 | 30 | 30 | 30 | 0 | 0 | 0 | 40 | 20 | 40 | - | -
5 | Others Project (Meeting, Presentation to Mgt) | Based on request | 1.698% |  |  | 55 | 9.1667 | 30 | 60 | 45 | 30 | 120 | 120 | 0 | 60 | 45 | 30 | 120 | 120 | 120 | 0 | 0 | 15 | 10 | 0 | 30 | - | -
|  | Total | 66.67% | 9 | 540 | 2160 | 360 | 540 | 540 | 540 | 540 | 540 | 540 | 0 | 120 | 540 | 540 | 600 | 600 | 540 | 0 | 0 | 540 | 540 | 540 | 540
|  | Available | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 420 | 0 | 0 | -60 | -60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 39

## Ashiqur Rahman (3)
Resource
Ashiqur Rahman
SL | Project | Activity | Engagement % Per-Day | Work Hour | Work Minute (Per Day) | Weekly Total (Minutes) | Engagement Per-Day (Minutes) | 2021-01-09 | 2021-01-10 | 2021-01-11 | 2021-01-12 | 2021-01-13 | 2021-01-14 | Total (min) | 2021-01-16 | 2021-01-17 | 2021-01-18 | 2021-01-19 | 2021-01-20 | 2021-01-21 | Total (min) | 1900-02-12 | 1900-02-13 | 1900-02-14 | 1900-02-15 | 1900-02-16 | 1900-02-17 | Total (min) | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | Total (min) | Remaining (Hours) | End Date
1 | Visitor Approval System | Requirement Analysis | 20.51% | 9 | 540 | 1440 | 110.7692 | 360 | 360 | 0 | 0 | 0 | 0 | 720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-02-28
2 | Security Guard App | Development | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 2021-03-31 |  | 0
3 | Bill Management App | Development | 71.37% |  |  | 5010 | 385.3846 | 60 | 60 | 420 | 420 | 420 | 420 | 1380 | 330 | 300 | 300 | 300 | 300 | 300 | 1500 | 480 | 480 | 480 | 480 | 480 | 480 | 2880 | 300 | 300 | 480 | 480 | 480 | 480 | 2520 | 12 | 2021-02-28 |  | 83.5
4 | AQL- Web Part (CR) | Development | [5 empty] | 60 | 60 | 60 | 60 | 60 | 60 | 300 | 180 | 180 | 180 | 180 | 180 | 180 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 180 | 0 | 0 | 0 | 0 | 360 | 0 | 2021-02-18
5 | Maintenance & Troubleshooting (Capex, ER, DEC Service Tracker, VAS, PMS, QMS, Hot Desking, IOU) | Troubleshooting | 7.265% |  |  | 510 | 39.2308 | 30 | 30 | 30 | 30 | 30 | 30 | 150 | 30 | 30 | 30 | 30 | 30 | 30 | 150 | 30 | 30 | 30 | 30 | 30 | 30 | 180 | 30 | 30 | 30 | 30 | 30 | 30 | 180 | - | 2021-02-28
6 | Others Project (Meeting, Presentation to Mgt) | Based on request | 6.838% |  |  | 480 | 36.9231 | 30 | 30 | 30 | 30 | 30 | 30 | 150 | 0 | 30 | 30 | 30 | 30 | 30 | 150 | 30 | 30 | 30 | 30 | 30 | 30 | 180 | 30 | 30 | 30 | 30 | 30 | 30 | 180 | - | -
|  | Total | 106% | 9 | 540 | 7440 | 572.3077 | 540 | 540 | 540 | 540 | 540 | 540 | 2700 | 540 | 540 | 540 | 540 | 540 | 540 | 2700 | 540 | 540 | 540 | 540 | 540 | 540 | 3240 | 540 | 540 | 540 | 540 | 540 | 540 | 3240
|  | Available | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48
51

## Rabi (hidden)
Resource
Rabiul Ali Sarker
SL | Project | Activity | Engagement % Per-Day | Work Hour | Work Minute (Per Day) | Weekly Total (Minutes) | Engagement Per-Day (Minutes) | 2020-12-12 | 2020-12-13 | 2020-12-14 | 2020-12-15 | 2020-12-16 | 2020-12-17 | 2020-12-18 | 2020-12-19 | 2020-12-20 | 2020-12-21 | 2020-12-22 | 2020-12-23 | 2020-12-24 | 2020-12-25 | 2020-12-26 | 2020-12-27 | 2020-12-28 | 2020-12-29 | 2020-12-30 | 2020-12-31 | Remaining (Hours) | End Date
1 | QMS (KQC) | Error Analysis | 1.389% | 9 | 540 | 150 | 7.5 | 30 | 30 | 30 | 30 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2020-12-17
2 | QMS (END Line) Birichina | CR & Development | 15.56% |  |  | 1680 | 84 | 420 | 420 | 420 | 30 | 0 | 30 | 0 | 30 | 30 | 30 | 30 | 30 | 30 | 0 | 30 | 30 | 30 | 30 | 30 | 30 | 0 | 2020-12-31
3 | QMS (AQL) | Design | 53.89% |  |  | 5820 | 291 | 0 | 0 | 0 | 390 | 0 | 390 | 0 | 420 | 420 | 420 | 420 | 420 | 420 | 0 | 420 | 420 | 420 | 420 | 420 | 420 | 84 | 2020-12-31
4 | Security Guard App | Development | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Maintenance & Troubleshooting (QMS Line In, Hourly Audit, GPQ) | Based on request | 9.444% |  |  | 1020 | 51 | 60 | 60 | 60 | 60 | 0 | 60 | 0 | 60 | 60 | 60 | 60 | 60 | 60 | 0 | 60 | 60 | 60 | 60 | 60 | 60 | - | -
6 | Others Project (Meeting, Presentation to Mgt) | Based on request | 4.722% |  |  | 510 | 25.5 | 30 | 30 | 30 | 30 | 0 | 30 | 0 | 30 | 30 | 30 | 30 | 30 | 30 | 0 | 30 | 30 | 30 | 30 | 30 | 30 | - | -
|  | Total | 85% | 9 | 540 | 9180 | 459 | 540 | 540 | 540 | 540 |  | 540 |  | 540 | 540 | 540 | 540 | 540 | 540 |  | 540 | 540 | 540 | 540 | 540 | 540
|  | Available | [5 empty] | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0

## Rabi (2)
Resource
Rabiul Ali Sarker
SL | Project | Activity | Engagement % Per-Day | Work Hour | Work Minute (Per Day) | Weekly Total (Minutes) | Engagement Per-Day (Minutes) | 2020-12-19 | 2020-12-20 | 2020-12-21 | 2020-12-22 | 2020-12-23 | 2020-12-24 | 2021-01-01 | 2021-01-02 | 2021-01-03 | 2021-01-04 | 2021-01-05 | 2021-01-06 | 2021-01-07 | 2021-01-09 | 2021-01-10 | 2021-01-11 | 2021-01-12 | 2021-01-13 | 2021-01-14 | 2021-01-15 | Remaining (Hours) | End Date
1 | QMS (KQC) | Error Analysis | 0% | 9 | 540 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2020-12-31
2 | QMS (END Line) Birichina | CR & Development | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2020-12-31
3 | QMS (AQL) | Development | 73.81% |  |  | 2790 | 398.5714 | 480 | 495 | 510 | 435 | 510 | 390 | 0 | 510 | 435 | 510 | 480 | 405 | 450 | 0 | 0 | 0 | 0 | 60 | 60 | 0 | 72 | 2021-01-31
4 | Security Guard App | Development | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 2021-03-31
5 | Maintenance & Troubleshooting (QMS Line In, Hourly Audit, GPQ) | Based on request | 4.762% |  |  | 180 | 25.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 45 | 30 | 30 | 45 | 0 | 0 | 60 | 45 | 30 | 120 | 120 | 120 | - | -
6 | Others Project (Meeting, Presentation to Mgt) | Based on request | 7.143% |  |  | 270 | 38.5714 | 60 | 45 | 30 | 45 | 30 | 90 | 0 | 0 | 60 | 0 | 30 | 90 | 90 | 0 | 60 | 45 | 30 | 180 | 180 | 120 | - | -
|  | Total | 85.71% | 9 | 540 | 3240 | 462.8571 | 540 | 540 | 540 | 540 | 540 | 540 | 0 | 540 | 540 | 540 | 540 | 540 | 540 | 0 | -60 | -45 | -30 | -180 | -180 | -120
|  | Available | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Rabi (3)
Resource
Rabiul Ali Sarker
SL | Project | Activity | Engagement % Per-Day | Work Hour | Work Minute (Per Day) | Weekly Total (Minutes) | Engagement Per-Day (Minutes) | 2020-12-26 | 2020-12-27 | 2020-12-28 | 2020-12-29 | 2020-12-30 | 2020-12-31 | Total | 2021-01-01 | 2021-01-02 | 2021-01-03 | 2021-01-04 | 2021-01-05 | 2021-01-06 | 2021-01-07 | Total | 2021-01-09 | 2021-01-10 | 2021-01-11 | 2021-01-12 | 2021-01-13 | 2021-01-14 | Total (min) | 2021-01-16 | 2021-01-17 | 2021-01-18 | 2021-01-19 | 2021-01-20 | 2021-01-21 | 2021-01-22 | Total (min) | 2021-01-16 | 2021-01-17 | 2021-01-18 | 2021-01-19 | 2021-01-20 | 2021-01-21 | Total (min) | 2021-01-23 | 2021-01-24 | 2021-01-25 | 2021-01-26 | 2021-01-27 | 2021-01-28 | Total (min) | Remaining (Hours) | End Date
1 | QMS (KQC) | Error Analysis | 4.762% | 9 | 540 | 360 | 25.7143 | 30 | 30 | 30 | 30 | 30 | 30 | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2020-12-17
2 | QMS (END Line) Birichina | CR & Development | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 480 | 60 | 0 | 0 | 0 | 540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 480 | 60 | 0 | 0 | 0 | 540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2020-12-31
3 | QMS (AQL) | Design | 107.1% |  |  | 8100 | 578.5714 | 450 | 450 | 450 | 450 | 450 | 450 | 2700 | 0 | 450 | 450 | 450 | 450 | 450 | 450 | 2700 | 480 | 0 | 420 | 480 | 480 | 480 | 2340 | 0 | 480 | 480 | 480 | 480 | 60 | 0 | 1980 | 480 | 0 | 420 | 480 | 480 | 480 | 2340 | 0 | 480 | 480 | 480 | 480 | 60 | 1980 | 0 | 2020-12-31
4 | Security Guard App | Development | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 420 | 480 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 420 | 420 | 150 | 2021-03-31
5 | Maintenance & Troubleshooting (QMS Line In, Hourly Audit, GPQ) | Based on request | 7.143% |  |  | 540 | 38.5714 | 30 | 30 | 30 | 30 | 30 | 30 | 180 | 0 | 30 | 30 | 30 | 30 | 30 | 30 | 180 | 30 | 30 | 30 | 30 | 30 | 30 | 180 | 0 | 30 | 30 | 30 | 30 | 30 | 30 | 180 | 30 | 30 | 30 | 30 | 30 | 30 | 180 | 0 | 30 | 30 | 30 | 30 | 30 | 150 | - | -
6 | Others Project (Meeting, Presentation to Mgt) | Based on request | 7.143% |  |  | 540 | 38.5714 | 30 | 30 | 30 | 30 | 30 | 30 | 180 | 0 | 30 | 30 | 30 | 30 | 30 | 30 | 180 | 30 | 30 | 30 | 30 | 30 | 30 | 180 | 0 | 30 | 30 | 30 | 30 | 30 | 30 | 180 | 30 | 30 | 30 | 30 | 30 | 30 | 180 | 0 | 30 | 30 | 30 | 30 | 30 | 150 | - | -
|  | Total | 126.2% | 9 | 540 | 9540 | 681.4286 | 540 | 540 | 540 | 540 | 540 | 540 | 3240 |  | 510 | 510 | 510 | 510 | 510 | 510 | 3060 | 540 | 540 | 540 | 540 | 540 | 540 | 3240 |  | 540 | 540 | 540 | 540 | 540 | 540 | 3240 | 540 | 540 | 540 | 540 | 540 | 540 | 3240 |  | 540 | 540 | 540 | 540 | 540 | 2700
|  | Available | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 30 | 30 | 30 | 30 | 30 | 30 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0

## Ashok
Resource
Ashok Toru Roy
SL | Project | Activity | Engagement % Per-Day | Work Hour | Work Minute (Per Day) | Weekly Total (Minutes) | Engagement Per-Day (Minutes) | 2020-12-12 | 2020-12-13 | 2020-12-14 | 2020-12-15 | 2020-12-16 | 2020-12-17 | 2020-12-18 | 2020-12-19 | 2020-12-20 | 2020-12-21 | 2020-12-22 | 2020-12-23 | 2020-12-24 | 2020-12-25 | 2020-12-26 | 2020-12-27 | 2020-12-28 | 2020-12-29 | 2020-12-30 | 2020-12-31 | Remaining (Hours) | End Date
1 | AMS | Troubleshooting & Request Handling | 9.444% | 9 | 540 | 1020 | 51 | 60 | 60 | 60 | 60 | 0 | 60 | 0 | 60 | 60 | 60 | 60 | 60 | 60 | 0 | 60 | 60 | 60 | 60 | 60 | 60 | - | -
2 | WFX BI Reporting | Training on BI | 26.67% |  |  | 2880 | 144 | 0 | 180 | 180 | 180 | 0 | 180 | 0 | 180 | 180 | 180 | 180 | 180 | 180 | 0 | 180 | 180 | 180 | 180 | 180 | 180 | 36 | 2020-12-31
3 | Others Project (Meeting, Presentation to Mgt) | Based on request | 4.722% |  |  | 510 | 25.5 | 30 | 30 | 30 | 30 | 0 | 30 | 0 | 30 | 30 | 30 | 30 | 30 | 30 | 0 | 30 | 30 | 30 | 30 | 30 | 30 | - | -
|  | Total | 40.83% | 9 | 540 | 4410 | 220.5 | 90 | 270 | 270 | 270 |  | 270 |  | 270 | 270 | 270 | 270 | 270 | 270 |  | 270 | 270 | 270 | 270 | 270 | 270
|  | Available | [5 empty] | 450 | 270 | 270 | 270 |  | 270 |  | 270 | 270 | 270 | 270 | 270 | 270 |  | 270 | 270 | 270 | 270 | 270 | 270

## Ashok (2)
Resource
Ashok Toru Roy
SL | Project | Activity | Engagement % Per-Day | Work Hour | Work Minute (Per Day) | Weekly Total (Minutes) | Engagement Per-Day (Minutes) | 2021-01-30 | 2021-01-31 | 2021-02-01 | 2021-02-02 | 2021-02-03 | 2021-02-04 | Remaining (Hours) | End Date
1 | AMS | Troubleshooting & Request Handling | 9.259% | 9 | 540 | 300 | 50 | 0 | 60 | 60 | 60 | 60 | 60 | - | -
2 | AMS Handover | Knowledge Transfer | 9.259% |  |  | 300 | 50 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 2021-01-31
3 | Bill Management UI Dev. | Development | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60
4 | Admin Pannel | Development | 44.44% |  |  | 1440 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 123
5 | Others Project (Meeting, Presentation to Mgt) | Based on request | 4.63% |  |  | 150 | 25 | 0 | 30 | 30 | 30 | 30 | 30 | 50 | -
|  | Total | 60.19% | 9 | 540 | 1950 | 325 | 0 | 630 | 330 | 330 | 330 | 330 | 50
|  | Available | [5 empty] | 0 | -90 | 210 | 210 | 210 | 210

## Ashok (3)
Resource
Ashok Toru Roy
SL | Project | Activity | Engagement % Per-Day | Work Hour | Work Minute (Per Day) | Weekly Total (Minutes) | Engagement Per-Day (Minutes) | 2021-02-06 | 2021-02-07 | 2021-02-08 | 2021-02-09 | 2021-02-10 | 2021-02-11 | Total (min) | 2021-02-13 | 2021-02-14 | 2021-02-15 | 2021-02-16 | 2021-02-17 | 2021-02-18 | Total (min) | Remaining (Hours) | End Date
1 | AMS | Troubleshooting & Request Handling | 15.38% | 9 | 540 | 1080 | 83.0769 | 60 | 60 | 60 | 60 | 60 | 60 | 360 | 60 | 60 | 60 | 60 | 60 | 60 | 360 | - | -
2 | Bill Management | UI Development | [5 empty] | 120 | 120 | 120 | 120 | 120 | 120 | 720 | 120 | 120 | 120 | 120 | 120 | 120 | 2880 | 0 | 2021-02-28
3 | Admin Pannel Development | Development | [5 empty] | 330 | 330 | 330 | 330 | 330 | 330 | 1980 | 330 | 330 | 330 | 330 | 330 | 330 | 5400 | 30 | 2021-02-15
4 | Others Project (Meeting, Presentation to Mgt) | Based on request | 7.692% |  |  | 540 | 41.5385 | 30 | 30 | 30 | 30 | 30 | 30 | 180 | 30 | 30 | 30 | 30 | 30 | 30 | 3420 | - | -
|  | Total | 23.08% | 9 | 540 | 1620 | 124.6154 | 540 | 540 | 540 | 540 | 540 | 540 | 3240 | 540 | 540 | 540 | 540 | 540 | 540 | 3240
|  | Available | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[24 empty] | Software Development Cycle | Responsible
[24 empty] | Requirement Collection | PM
[24 empty] | Requirement Analysis | PM+SM
[24 empty] | Solution Design | SM+Developer
[24 empty] | Development | Developer
[24 empty] | Implementation | Implementaion Team
[24 empty] | User Acceptance Test | PM
[24 empty] | Handover | PM+SM
3600
60

## ResourceEngagementSummary
[5 empty] | Running |  |  |  | Completed |  |  | Paused
|  |  |  | Dec'20 |  | Jan'21 |  |  |  | Feb'21
Sl | Resource | Project | Target Compleation Date | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
1 | Ashiqur | Visitor Approval System | 2021-01-10 | bar: Dec'20 W3 to Jan'21 W2
|  | Bill Management System | 2021-01-31 | bar: Jan'21 W1 to Jan'21 W4
|  | Security Guard App | 2021-03-31 | bar: Feb'21 W1 to Feb'21 W4
|  | QMS (AQL) - Web application part | 2021-01-31 | bar: Jan'21 W2 to Jan'21 W4
|  | Maintenance & Troubleshooting (Capex, ER, DEC Service Tracker, VAS, PMS, QMS, Hot Desking, IOU) | 2021-01-31 | bar: Dec'20 W3 to Jan'21 W4
2 | Robi | QMS (KQC) | 2020-12-31 | bar: Dec'20 W3 to Dec'20 W4
|  | QMS (END Line) Birichina | 2020-12-31 | bar: Dec'20 W3 to Dec'20 W4
|  | QMS (AQL) - Apps part | 2021-01-31 | bar: Dec'20 W3 to Jan'21 W4
|  | Security Guard App | 2021-03-31 | bar: Feb'21 W1 to Feb'21 W4
|  | Maintenance & Troubleshooting (QMS Line In, Hourly Audit, GPQ) | -
3 | Ashok | Bill Management (User Interface Design) | 2020-12-31 | bar: Dec'20 W4 to Jan'21 W2
|  | Admin Pannel for AMS System | 2021-02-15 | bar: Jan'21 W2 to Jan'21 W4
|  | WFX BI Reporting / Power BI Dashboard | 2020-12-31 | bar: Dec'20 W3 to Dec'20 W4
|  | AMS Maintenance & Troubleshooting (Capex, ER, DEC Service Tracker, VAS, PMS, QMS, Hot Desking, IOU) ) | -
|  |  |  | 4/5 API | Login API Done
Report API
View Interface

## Sheet1 (hidden)
| Strategic Role | Engagement (%) | Avg. Hrs / Day |  | Working Hour Distribution | Hours
1 | ERP Business Analyst | 20 | 3 |  | Business Related Meeting | 2
2 | ERP System Administrator | 5 | 1 |  | Projects Planning & Coordination | 3
3 | Software Development Lead | 25 | 3 | 5 | Software Development Coordination | 3
4 | Assistant Solution Architect for Digitization | 20 | 2 |  | Internal Meetings | 3
5 | Technical Analyst of Software Change Mgt. | 20 | 3 | 3
6 | Assisting RPA Automation for ERP data entry | 10 | 1 |  | Total | 11
| Total | 100 | 13